## Sheet1
Risk Assessment | Description | Risk | Current prevention | Potential prevention | Response | Impact | Tolerance
Risk:
Hardware is corrupt/destroyed/lost | HARD DRIVE COULD DIE. Any hardware being used for the project could break or die resulting in a loss of data. Despite GitHub and other cloud methodologies, with it being server based and reliant on plugins and dependencies this could impact the project. | Med | All code has been consistently backed up onto GitHub and saved on iCloud. | Make sure the hardware is in the best possible condition and used correctly to prevent any damage. | Try and fix/replace the hardware as soon as possible and begin to recover the work in progess. | High | Tolerate
Powercut | There could be a power cut in the location of where the project is taking place. With the server being run locally this would shut down the database and therefore the data. | Low | Currently no prevention | Is the project was super important/people were relying on the server then a backup power source could be investigated. | Try and get power back or initiate the backup plan. | Medium | Tolerate
Loss of power or a system restart/update | Because the project communicates with a h2 database, if the computer running the local database for numerous reasons shuts down the database will also be lost. | Low | The PC is constantly plugged to power being a tower. All windows updates are scheduled for later in the day. | Automatic updates could be turned off just to be sure | Turn the computer back on and start the h2 up again as soon as possible | Medium | Tolerate
Software error | The programmes used for the project: Postman, Spring, any IDE's and even JDK, Maven, JUnit etc could corrupt or show an error preventing use. The project relies on many programmes and if one or two were to have errors it could significantly impact the project. | Med | Making sure programmes are backuped or have a recovery point so that if there was an error that couldnt be quickly diagnosed and fixed you could restore to a working version. | A backup machine or laptop with the programmes pre installed could be useful for a desperate situation where there is no immediate fix | Run a troubleshooter and try to diagnose the error as soon as possible. If not then move to another machine that has or can get the programme. | Low | Tolerate
Java error - that isnt recognised | Because I am a trainee programmer, there is the possiblity that I encounter a new error or an error that I don't know how to fix. This would impact the project as I could be at a standstill and wouldn't be able to progress without getting over the hurdle. | High | I have made sure I have contact details for my course leader and I know how to use the internet well to help me solve problems effectively and quickly. | Making sure I do as much research and ask lots of questions to help better my understanding of the language and programmes I use: Spring etc | If I am at a point where I don't know how to fix or solve an error, I will use the internet to try and give me some insight. Failing that I will contact my course leader for some instruction. | High | Tolerate